## Summary
Suggested Open Data Deliverables and Actions for Greater Manchester
Version: | 1.2
Date: | 2021-01-22
What is this document?
This document sets out the key deliverables and actions that Greater Manchester must, should and could take in order to open more data and build a better information ecosystem. These actions have been created based upon the research and findings of our Local Data Review.
How to navigate this document
GM Deliverables
1. This tab shows the high level deliverables for the region. 2. These are prioritised according to a MoSCoW framework, with 'must haves' listed as the essential steps that must be taken first. These are then supported by second priority 'should haves', and by third priority 'could haves'. 3. Deliverables are coded and linked to show how they are all supported by, or further developed by, other deliverables. 4. Deliverables are also linked to specific supporting actions, which shows the practical steps that must be taken to achieve these deliverables.
Supporting actions
1. This tab shows the more detailed step by step actions that must be taken in order to achieve the deliverables set out in the GM Deliverables tab. 2. As above, these actions are all coded and linked to specific deliverables from the previous tab. 3. Where these actions relate to a specific case study from our Local Data Review analysis, these case studies have been mentioned to provide additional context.
Key considerations
It is important to remember that these findings are subjective and are based upon research carried out to date. These actions and deliverables can be amended at any time in light of new findings - either with the addition or deletion of specific actions or deliverables, or through the reorganisation of priorities.

## GM Deliverables
Deliverables |  |  |  |  | Supporting actions
Code | Deliverable | MoSCoW priority rating: | Developed further by: | Builds upon:
M1 | Open more datasets, from more organisations, that users want and need | Must have | S6 |  | CO1 D1 D11 D13
M2 | Put in place a programme of work to identify, prioritise and support new data releases | Must have | S6 S1 C9 |  | CO1 CO2 CU3 D1 D14 DM1 DM3
M3 | Create an easily accessible place to share open data for each public sector organisation in Greater Manchester | Must have | S3 C1 |  | D9
M4 | Develop and agree upon a set of basic standards for the highest priority datasets | Must have | S2 |  | D11 LS1 LS2
M5 | Establish a central repository that lists and describes all datasets held by the public sector in Greater Manchester | Must have | S5 C7 |  | CA2 DM3
M6 | Agree to open data in accessible, open formats | Must have | C1 C8 |  | D4 D5 D21 LS6
M7 | Establish an inclusive governance framework for open data across Greater Manchester | Must have | S4 S1 |  | DM1 SU7
M8 | Create an effective communication strategy that articulates the value and purpose of open data | Must have | S9 C11 |  | CU3 DM1 DM3 LSA5
M9 | Listen to and engage with data users, starting now | Must have | S7 |  | CA1 CA7
M10 | Make the case for open data releases that will support business growth and innovation in Greater Manchester | Must have | S6 S7 |  | CA4 CO1 CU1 CU5
M11 | Ensure open data is embedded in all policy areas in Greater Manchester | Must have | S8 S10 |  | CO1 CU1 CU5
M12 | Lay out an open data roadmap - an action plan - for the Greater Manchester public sector | Must have | S8 S1 C11 |  | LSA5 CA7
S1 | Create a pan-Greater Manchester portfolio for data and information, covering data use, information governance, research and analysis | Should have | C9 | M2 M7 M8 | LSA1 LSA2 SU3
S2 | Create a standards board for Greater Manchester, paying consideration to the trade-off between capacity and standards | Should have |  | M4 | LSA1 LSA6 LS5
S3 | Create a Greater Manchester-wide datastore | Should have | C1 C6 C10 | M3 | DM5 DM6 SU1 D17 D19 D20
S4 | Establish a Greater Manchester-wide process for opening data that includes information governance considerations | Should have | C3 C9 | M7 | DM4 LSA1 LS4 DM8
S5 | Expand the level of detail in the central metadata repository | Should have | C7 | M5 | D12 D18 LS4
S6 | Emphasise the curation, rather than simply the opening, of datasets | Should have | C2 C4 | M1 M2 | D10
S7 | Review the use of published data and design evaluation mechanisms to understand how data is being used | Should have | C2 | M10 | CO3 D10 LSA2 SU2 SU3
S8 | Ensure each organisation has set their own open data policy | Should have | C3 | M8 M12 | LSA4 SU1
S9 | Widely promote open data through different approaches | Should have | C4 C5 C11 | M9 | CA3 SU1 SU5
S10 | Treat open data infrastructure as essential infrastructure | Should have |  | M12 | DM5 DM6 LSA4 LSA6
S11 | Engage with the open data community through approaches such as hackathons or innovation days | Should have | C5 | M10 M11 | CA5 CA6 CU4
C1 | Build visualisation and open analysis features into the datastore | Could have |  | M3 M6 S3 | CU4 D3 D6 D8
C2 | Actively collaborate with the Local Enterprise Partnership, Chamber of Commerce and other private sector organisations to understand open data preferences in the business community | Could have |  | M10 M11 S6 S7 | CO4 CU4 SU4
C3 | Create an agreed Greater Manchester-wide open data policy, setting out the approach, responsibilities and prioritised data to release | Could have |  | S4 S8 | D15 LSA3 CU2
C5 | Encourage developers to engage with data and discover new ways of using it | Could have |  | S6 S9 | CA5 CA6 CU4 SU6
C6 | Migrate to an in-house data portal over time, where the content and infrastructure is controlled by the public sector | Could have | C10 | S3 | D2 D8 DM7 LS3
C8 | Work towards providing data to 5 star level open data as skills and awareness within and outside the public sector matures | Could have |  | M6 | CO4
C9 | Embed data leads within senior leadership | Could have |  | M2 S1 S4 | LSA3
C10 | Consider segregating the front end data portal into different sections to cater to multiple audiences | Could have |  | S3 C6 | CO4 LS3 DM7
C11 | Use the approach to open data as a chance to showcase Greater Manchester as a digital region | Could have |  | M8 M9 S9 | CO5
C12 | Consider ways to share more sensitive and closed data, such as health data, alondside traditional open data | Could have |  | S3 | DM9 DM10 D22 D23
C13 | Support SMEs, VCSEs and other smaller organisations in accessing and using public sector data more effectively | Could have |  | S6 | CO4 D16 SU6

## Supporting actions
Action Code | Action | Theme | Related to deliverable: | Link to relevant case study for context (where applicable)
CA1 | Create a strong communication strategy to guide data releases. | Communications and awareness | M8
CA2 | Develop a central repository of metadata for all datasets, where information is stored in different places | Communications and awareness | M5 | London Datastore
CA3 | Create ‘data drops’ to communicate new data releases more widely | Communications and awareness | S9 | Food Standards Agency
CA4 | Build a feedback function to gain insights into how users interact with the site and data, and to draw out possible additional features | Communications and awareness | M9 | NationalMap
CA5 | Design and hold hackathons to increase demand for datasets and find new uses for them | Communications and awareness | C4 C5 | Data Mill North
CA6 | Design and hold innovation days to offer fresh perspectives from the wider community | Communications and awareness | C4 C5 | Data Mill North
CA7 | Create use cases to demonstrate how open data can be used commercially or to improve the city region | Communications and awareness | M8 | Copenhagen Data Exchange
CO1 | Hold conversations with the business community to establish the data needs of the potential user base | Commercialisation | M1 M2 M9 M10 | London Datastore
CO2 | Create a prioritisation matrix for new data requests | Commercialisation | M2
CO3 | Consider the equalities impact of opening data | Commercialisation | S7 | Copenhagen Data Exchange
CO4 | Identify and create measures to support SMEs in accessing and using data | Commercialisation | C2 C8 C10 C13 | Copenhagen Data Exchange
CO5 | Build a northern-wide infrastructure pipeline to draw attention to the North as a place worth investing in | Commercialisation | C11 | ANZIP
CU1 | Attend local events to build links with the grassroots data community | Culture | M9 M10
CU2 | Designate a member of staff in each department to be tasked with data publication | Culture | C3
CU3 | Create a guiding set of open data principles | Culture | M2 M11
CU4 | Encourage the public to pitch analytics projects directly | Culture | C1 C2 C4 C5
CU5 | Provide a feedback platform for open data | Culture | M9 M10
D1 | Source and identify datasets to publish | Data | M1 M2
D10 | Run regular consultations with key stakeholders to identify the most useful and needed datasets | Data | S6 S7 | London Datastore
D11 | Provide metadata for each dataset released, giving the name, explanation for the data, licence and key contact | Data | M1 M4 | MappingGM
D12 | Create a complete and comprehensive list of metadata | Data | S5 | Food Standards Agency
D13 | Create a programme of work to support more open data releases | Data | M1
D14 | Identify a pipeline of data to be released | Data | M2
D15 | Create a clearly articulated use case for each dataset | Data | C3
D16 | Curate collections of datasets of benefit to VCSE organisations that do not have the capacity to search through different datasets | Data | C13
D17 | Enable GM data that is sent to central government for collation and release to be made available locally in advance | Data | S3
D18 | Ensure that a data publication schedule is included with the data | Data | S5
D19 | Allow data re-users to sample or preview the data before committing to download entire datasets | Data | S3
D2 | Build a Greater Manchester dashboard with a comprehensive overview of region metrics (e.g. health, unemployment, economic performance etc) | Data | C6 | NOLAlytics
D20 | Make data available through an API where appropriate | Data | S3 C10
D21 | Create persistent links for datasets to minimise broken data links | Data | M6
D22 | Explore the viability of creating synthetic data for sensitive and protected data | Data | C12
D23 | Create a health data sandbox | Data | C12
D3 | Create visualisations and interactive maps to enhance usability and allow users to explore data on their own terms | Data | C1 | MappingGM
D4 | Provide data in more than one format | Data | M6
D5 | Provide data to at least 3 star open data level | Data | M6
D6 | Publish contextual narrative about the background of datasets and what they relate to | Data | C1 C7 | European Data Portal
D7 | Provide data to at least 5 star open data level | Data | C8 C10
D8 | Show open analysis on GM data | Data | C1 C6
D9 | Create a website or decide on another location to host the data | Data | M3
DM1 | Designate responsibility for open data to a specific team | Data management | M2 M7 M12
DM10 | Develop best practice guidelines regarding data anonymisation and other privacy enhancing techniques | Data management | C12
DM3 | Clearly define ownership of different datasets | Data management | M2 M5 M12 | Insight Cheshire East
DM4 | Have data stewards or data champions to ensure that data is managed effectively | Data management | S4
DM5 | Consider and select appropriate technology to host and share data (e.g. CKAN, Socrata etc) | Data management | S3 S10
DM6 | Build and maintain a Greater Manchester-wide datastore | Data management | S3 S10
DM7 | Build and maintain an in-house rather than external data portal, to improve data oversight and flexibility | Data management | C6 C10
DM8 | Embed an IG team member in the open data team in organisations across the region | Data management | S4
DM9 | Invest in full-time data managers with a remit to release GM NHS data | Data management | C12
LS1 | Create a process to ensure that data publishers follow the basic data standards checklist | Licencing and standards | M4
LS2 | Create a basic data standards checklist | Licencing and standards | M4
LS3 | Give clear consideration to the balance between portal size and its subsequent impact on standards | Licencing and standards | C6 C10 | EU Open Data Portal
LS4 | Create a Greater Manchester wide governance framework for data and metadata standards | Licencing and standards | S4 S5
LS5 | Create use cases to illustrate the value of standards in order to motivate data owners to subscribe to higher standards | Licencing and standards | S2
LS6 | Ensure that open licenses relevant to the data are explicit | Licencing and standards | M6
LSA1 | Include open data as a standing item on information board | Leadership and strategic alignment | S1 S2 S4
LSA2 | Design appropriate KPIs to keep track of the direction and outcomes of open data | Leadership and strategic alignment | S1 S7 | NYC Analytics
LSA3 | Designate specific responsibility for information (IG, open data etc) to a senior leader or embed data leads within senior leadership | Leadership and strategic alignment | C3 C9
LSA4 | Create an organisation-wide open data policy, setting out approach, responsibilities and data to release | Leadership and strategic alignment | S8 S10
LSA5 | Align the open data agenda with wider strategic priorities for the region | Leadership and strategic alignment | M11 M10
LSA6 | Create a standards board for Greater Manchester | Leadership and strategic alignment | S2 S10
SU1 | Automate updates as far as possible | Sustainability | S3 S8 S9 | Ordnance Survey
SU2 | Design evaluation mechanisms to understand how data is being used | Sustainability | S7
SU3 | Review the use of published data and make relevant changes | Sustainability | S1 S7 | Salford Data Quay
SU4 | Create and maintain an Active Use Typology to keep track of the usage of existing data sets | Sustainability | C2 | NOLAlytics
SU5 | Share open data releases and use cases on social media | Sustainability | S9
SU6 | Create a shared repository of tools built on published data | Sustainability | C5 C13
SU7 | Create a process to encorporate the voices of businesses, academia and VCSOs in open data governance | Sustainability | M7